## Logistics
50501 - The People's Movement: Protest Planning Sheet |  |  | NOTE: This is not a list of requirements, just a resource and a tool, and not all lines will apply in all jurisdictions. RALLY NAME/OBJECTIVE:
Timeline | Task | Point Person/s | Status | Date Done | Additional info | Time Needed to Finish | Notes
3 Weeks Before | Apply/Obtain a permit |  | Not started
3 Weeks Before | Set up Signal or other chat specific to rally for detailed planning and communications |  | Not started
3 Weeks Before | Save the Date - Notify all contacts |  | Not started
3 Weeks Before | Request/Confirm Legal Observers |  | Not started
3 Weeks Before | Promote on social and digital channels |  | Not started
3 Weeks Before | Identify potential sponors and ask for donations |  | Not started
3 Weeks Before | Distribute fliers locally |  | Not started
3 Weeks Before | Plan audio, what size PA System and where to get it from |  | Not started
3 Weeks Before | Organize transportation for community accessibility |  | Not started
3 Weeks Before | Identify security risks and strategies to protect group |  | Not started
3 Weeks Before | Plan for ASL/other interpreters |  | Not started
2 Weeks Before | Recruit volunteers and assign roles |  | Not started
3 Weeks Before | Identify list of speakers |  | Not started
2 Weeks Before | Recruit emcee, develop chants, program, opening/closing remarks etc |  | Not started
2 Weeks Before | Invite community speakers |  | Not started
2 Weeks Before | Recruit a Police Liaison, have copies of permits ready to have on hand during the protest |  | Not started
2 Weeks Before | Create schedule for day-of rally |  | Not started
1 Week Before | Keep eye on the weather and plan for alternatives if forecast is bad |  | Not started
1 Week Before | Host a poster/art making session |  | Not started
1 Week Before | Obtain/Coordinate/Set up food and water |  | Not started
1 Week Before | Develop and Schedule Media Advisory, send as early as possilbe and the morning of at 6:00am |  | Not started
1 Week Before | Develop and schedule reminders 1 day out and day of event - Notify all contacts |  | Not started
1 Week Before | Recruit Photographers/Videographers/Streamers |  | Not started
1 Week Before | Plan for PA setup and make sure voluteers are ready to set up early |  | Not started
1 Week Before | Find someone to ASL Livestream with the equiptment needed |  | Not started
Day Of Action | Set up media / medic / others areas |  | Not started
Day Of Action | Link ASL Livestream to LinkTree |  | Not started
Day Of Action | Set up on site route markers and/or volunteers |  | Not started
Day Of Action | Set up tables, information centers, sign making station, etc |  | Not started
Day Of Action | Have volunteer meeting so everyone is familiar with their roles and get comms set up for the event |  | Not started
Day Of Action | Bring PA System and set up |  | Not started
Post-Action | Schedule a post-action call to debrief |  | Not started
IMPORTANT NOTES |  |  | IMPORTANT LINKS
|  |  | Graphics | https://www.canva.com/design/DAGflLLPAOs/ap680JyJwLdQuYIVlMUO3A/view?utm_content=DAGflLLPAOs&utm_campaign=designshare&utm_medium=link&utm_source=publishsharelink&mode=preview
Meeting Agenda
|  |  | List Your 50501 Event | https://docs.google.com/forms/u/1/d/e/1FAIpQLSd0YaPAQqxdBYFwfmRNLI0PCKccD25WB2-V21ABAe3O1GuxLg/viewform

## Communications
Communications |  |  | RALLY NAME/OBJECTIVE
Task | Point Person/s | Status | Due Date | Additional Info | Notes
GRAPHICS
Create main flyer to be used for wide distribution |  | Not started
Create additional graphics to share goals and demands, how to participate |  | Not started
Create map for how people get to action site from public transport/parking |  | Not started
COMMUNITY OUTREACH
Collect peoples' stories in video or writing before rally |  | Not started
Reach out to each orgs to inform of rally and invite to collab, give toolkit |  | Not started
Invite elected officials to particpate/observe and request meetings before or after action |  | Not started
Print flyers to distribute around city |  | Not started
Distribute/hang flyers |  | Not started
PRESS
Contact popular radio stations |  | Not started
Contact print/online news outlets |  | Not started
Monitor press articles before and after action |  | Not started
SOCIAL MEDIA
Compile social media toolkit |  | Not started
Contact popular local social media influencers |  | Not started
Create Facebook event (need FB page) |  | Not started
Identify who will livestream action and through which accounts |  | Not started
Identify who will take and publish photos/videos of action |  | Not started
WRITING
Write a press release |  | Not started
Write talking points |  | Not started
Translate materials if needed |  | Not started
Write op-eds to local newspaper |  | Not started
Create/print info sheet to distribute to press during action |  | Not started
Media List
Graphics
Meeting Agenda

## Outreach
Team Info |  |  | RALLY NAME/OBJECTIVE
Organization/Community Group | Person Reaching Out | Date Contacted | Contact | Notes

## Volunteer
Team Info |  |  | RALLY NAME/OBJECTIVE
Volunteer Role Info https://www.thedirectactionmovement.com/supportiveroles
Volunteer Name | Role | Phone Number | Email | Notes
350 South Florida

## Chants
Chants (some examples here, take or leave them) | RALLY NAME/OBJECTIVE
Chant Ideas | Standalone Chants
Hey, hey, ho, ho! Elon Musk has got to go!”
7. No kings! No gods! No billionaire frauds!
2. Leader: Billionaires steal, billionaires lie!
Crowd: We won’t bow, we won’t buy!
8. Elon lies, Trump incites—
We won’t stop, we’ll stand and fight!
3. Leader: Truth is dying—who’s to blame?
Crowd: Musk and Trump, they play the game!
9. Not your cult, not your sheep—
Take your Doge and take a leap!
4. Leader: Doge to the moon, freedom to the grave!
Crowd: Billionaires won’t make us slaves!
10. Keep your bots, keep your hate—
Democracy won’t take the bait!
5. Leader: Twitter died, and what was left?
Crowd: Hate, lies, and a Nazi mess!
11. Tech bros, tax cheats, fascists too—
We see all the shit you do!
6. Leader: Who funds fascists, plain to see?
Crowd: Musk and Trump, the enemy!
12. One vote, one voice—
7. Leader: Who elected Presiden Musk? | Not your toy, not your choice!
Crowd: Nobody elected President Musk! - contributed by Val
13. America’s not for sale—
Elon, Trump, you’re bound to fail!
Down with Trump
Down with Musk
Down with kings | 14. We are the people, we are the wall—
Congress stand up | Billionaire greed will fall!
Gesture to go with it:
Down with Trump/Musk/Kings - Arm above head with hand in thumbs down position | 15. Truth matters, facts stay—
Keep your lies the hell away!
Congress stand up - Arm above head with hand in thumbs up position
(suggestion: Be VERY CAREFUL never to have an open hand extended. The Regressives _will_ take any such image out of context)
50501 is you, 50501 is me.
50501 is us, 50501 is free!

## Location
Team Info |  |  | RALLY NAME/OBJECTIVE
Task | Point Person/s | Status | Due Date | Additional Info | Notes
SCOUTING
Come up with a potential location option or options
Come up with a potential route option or options (if marching)
Check out the on the ground perspective for any routes being consdiered
Consider escape routes in case of a worst case scenario (police kettle bell, Nazi couter protester mob, etc)
COMMUNICATIONS
Develop a map
Share the map
Print a few copies of the map, or better yet make a short link, to have on hand for voluteer reference and people asking about the route
EXECUTION
Get supplies for on site route markers and/or recruit route volunteers
Screeshot of Map Of Location | Marching Route (if marching)

## Supplies
Supply List |  |  | RALLY NAME/OBJECTIVE
Item | Name | Name | Name

## Resources
Chapter Resources |  |  | RALLY NAME/OBJECTIVE
Description of Resource | Additional Info | Contact

## LATER questions
Questions For Later |  |  | RALLY NAME/OBJECTIVE
Question | Answer | Additional Info

## Team
Team Info |  |  | RALLY NAME/OBJECTIVE
Name | Role | Phone/Signal/Discord | Email
Subcomittee | Lead Coordinator
Funding
Safety
Comms
Volunteer
Outreach
Set Up/Break Down